## Sheet1
Sprint-1 (5 Working Days)
Day | Animesh | Ipsita | Nikhil | Satayu | Akshay | Daily Outcome
Day 1 | Create GitHub repo, React project, Routing setup | Analyze Hotel & Amenity requirements | Analyze Room & Room Type requirements | Analyze Reservation requirements | Analyze Payment & Review requirements | Requirement analysis, GitHub setup, project setup, db.json structure finalized
Day 2 | Build Dashboard & Routing | Create Hotel pages UI | Create Room pages UI | Create Reservation pages UI | Create Payment & Review pages UI | All page layouts ready with navigation
Day 3 | Integrate common components & review code | Hotel CRUD UI + connect to JSON | Room CRUD UI + connect to JSON | Reservation CRUD UI + connect to JSON | Payment & Review CRUD UI + connect to JSON | All modules connected with JSON Server
Day 4 | Merge branches & integration | Improve Hotel UI, validation, search | Improve Room UI, availability badges | Improve Reservation forms & filters | Improve Payment status & Review ratings | Fully integrated application with polished UI
Day 5 | Final integration, GitHub merge, presentation | Testing Hotel & Amenity modules | Testing Room modules | Testing Reservation module | Testing Payment & Review modules | Bug-free demo, responsive UI, sprint review ready